## Burn Down Chart
Project: | Hotel Booking System
Sprint # | 4
[5 empty] | DATE: | 2024-07-12 | 2024-07-13 | 2024-07-14 | 2024-07-15 | 2024-07-16 | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-20 | 2024-07-21
| User Story ID | User Story | Task | Assigned To | Estimate (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 10
| 15 | As a developer, I want to have the UI and functionality tested so that I can assure application is working as needed for users. | Perform Function testing | Arleth | 6 | 0 | 0 | 0 | 0 | 0 | 6 |  | 0 | 0 | 0
|  |  | Perform nonfunctional testing | Arleth | 4 | 0 | 0 | 0 | 0 |  | 4 | 0 | 0 | 0 | 0
| 16 | As a developer, I want to document the application design and overview so that others can easily understand and work on the application | Document Design | Arleth | 6 | 0 | 0 | 0 | 0 |  | 0 | 0 | 6 | 0 | 0
|  |  | Document Testcases | Arleth | 4 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 4 | 0
| Ideal - Remaining efforts in uninterrupted working hours. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual - Remaining efforts in uninterrupted working hours. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | -10 | -10 | -16 | -20 | -20
[9 empty] | Percent of User Stories complete for this iteration: |  |  |  |  | 100% | 2/2
[9 empty] | Percent of User Stories complete for entire project: |  |  |  |  | 100% | 16/16

## Project Backlog
Project Title: Hotel Booking System Functional
User Stories
ID | Feature | As a(n) <actor> | I would like to <description> | So that <outcome> | Estimate | Assigned To | Sprint #
1 | Registration | As a User | I would like to register on website before login | so that I can get a username and password | 5 | Arleth | 2
3 | Login | As a User | I would like to input my username | so that I can access website | 5 | Arleth | 2
4 | Login | As a User | I would like to input my password | so that I can access website | 5 | Arleth | 2
5 | Hotel Page | As a User | I would like to view available hotels and details | so that I can make an informed decision | 7 | Arleth | 2
6 | Hotel Page | As a User | I would like to be able to book available rooms | so that I can make a reservation | 7 | Arleth | 2
7 | Reservation Page | As a User | I would like to view my indivdual reservations | so that I can manage my bookings | 7 | Arleth | 2
8 | Reservation Page | As a User | I would like to be able to cancel my individual reservations | so that I can manage my bookings | 7 | Arleth | 2
9 | Database Creation | As a developer | I would like to create a database schema that stores information about hotels, rooms, reservations | so that I can store and read hotel information | 8 | Arleth | 1
10 | Database Creation | As a developer | I would like to create a database schema that stores information about users | so that I can store and read user information | 8 | Arleth | 1
11 | Hotel API | As a developer | I want to create a Hotel API for services such as booking, canceling and viewing | to enhance the functionality of the booking system. | 10 | Arleth | 1
12 | Hotel API | As a developer | I want to integrate a Hotel API for services such as booking, canceling and viewing | to enhance the functionality of the booking system. | 10 | Arleth | 1
13 | UI | As a devloper | I want to have a user-friendly UI | to allow users to easily use the site | 5 | Arleth | 3
14 | Registration | As a developer | I want to implement validation rules to the signup page | so that users can have complicated passwords. | 5 | Arleth | 3
15 | SIT Testing | As a developer | I want to have the UI and functionality testes | so that I can assure application is working as needed for users. | 10 | Arleth | 3
16 | Documentation | As a developer | I want to document the application design and overview | so that others can easily understand and work on the application | 8 | Arleth | 4

## How To Use
Step 1 | Hold a Sprint Planning meeting on Day 1 of of your Sprint where you will complete or update your User Stories as well as (re)prioritize your User Stories in your Product Back Log (ideally this should be done for the next 3-4 Sprints)
Step 2 | Copy the User Stories you plan to complete for this Sprint into your Sprint Back Log
Step 3 | Copy the User Stories you plan to complete from your Sprint Back Log into Column C
Step 4 | Break the User Story into a series of step by step development tasks in Column D
Step 5 | Estimate the User Story (in 1, 2, 4 or 8 Effort Man Hours) in Column F and if the task is larger than 8 hours break the User Story into multiple User Stories
Step 6 | Assign the User Story to a single Team Member in Column E
Step 7 | Repeat steps 4-6 for each User Story that has been planned for this Sprint
Step 8 | At the end of each day each Team Member should update the effort hours that were worked on their User Story to burn their work down
Step 9 | After each Daily Standup each Team Member should review the Burn Down Chart to ensure your Sprint will be delivered on time